## Sheet1
Task | Developer | Start Date | End Date | Duration
Requirement Analysis | Abdur Rehman | 2024-12-01 | 2024-12-05 | 4
System Design | Rehan Ahmed | 2024-12-25 | 2025-01-05 | 11
Database Setup | Mahad Ahmad | 2025-01-07 | 2025-01-15 | 8
Front-end Development | Abdur Rehman | 2025-01-17 | 2025-01-25 | 8
Back-end Development | Rehan Ahmed | 2025-01-26 | 2025-02-05 | 10
Integration and Testing | Mahad Ahmad | 2025-02-05 | 2025-02-10 | 5
Release | Abdur Rehman | 2025-02-11 | 2025-02-20 | 9